## AUT_participants_modules
Batch: | V & V Testing Banglore Aug 2025
Sprint Date: | 6th Nov 2025 - 18th Nov 2025
Application Under Test: | Apollo 24/7
S.No | Associates Name | Module undet test | BR_ID
1 | Vemula Akhilarani | Shop By Category | BR_Apollo24/7_ShopByCategory_01
2 | Naraboina Sneha | Lab Tests | BR_Apollo24/7_LabTests_02
3 | Koyyada Anvitha | Circle Membership | BR_Apollo24/7_CircleMembership_03
4 | J Sai Priya | Find Doctors | BR_Apollo24/7_FindDoctors_04
5 | Mogilipuri Varshitha | Buy Medicines | BR_Apollo24/7_BuyMedicines_05
Group Leader: | Vemula Akhilarani

## User Story
Application Under Test: | Apolo24/7
Module: | Lab Tests
| Epic | User story Id | User Story | Acceptance criteria
| Epic_01 Lab Tests Functionality | US_Apollo24/7_LabTests_01 | As a user, I want to view all lab tests, so that I can choose the right one. | 1.The user should be able to click on Lab Tests from the homepage. 2.The system should display a page listing all available lab tests. 3.The user should be able to navigate to Top Booked Tests and click View All. 4.The page should load completely with all expected elements visible.
|  | US_Apollo24/7_LabTests_02 | As a user, I want to sort and filter tests so that I can find affordable options. | 1.The user should be able to access the Sort By dropdown on the Lab Tests page. 2.The user should be able to select Price: Low to High and see tests sorted accordingly. 3.The user should be able to apply filters like Top Deals, Tests, and Packages, and the filters should persist.
|  | US_Apollo24/7_LabTests_03 | As a user, I want to be able to add tests to my cart and proceed to checkout so that I can complete my booking easily. | 1.The user should be able to click on the Add button for any test. 2.The system should update the cart count immediately after adding a test. 3.The user should be able to view the added test in the cart and proceed to checkout.

## Test Scenarios
Test Scenario
S.No | Module | Test Requirement Id | Test Scenario Id | Test Scenario Description
1 | Lab Tests and View All Functionality | TR_Apollo 24/7_Lab Tests_01 | TS_Apollo 24/7_Lab Tests_01 | To verify navigation from Homepage to Lab Tests and validate page load and “View All” button functionality.
2
3
1 | Sort By Functionality | TR_Apollo 24/7_Lab Tests_02 | TS_Apollo 24/7_Lab Tests_02 | To verify list display and sorting functionality, including “Sort By” dropdown and applying “Price: Low to High” option.
2
3
4
1 | Filters Functionality | TR_Apollo 24/7_Lab Tests_03 | TS_Apollo 24/7_Lab Tests_03 | To verify applying filters such as “Top Deals,” “Tests,” and “Packages,” and ensure all selected filters persist after application.
2
3
4
1 | Cart Functionality | TR_Apollo 24/7_Lab Tests_04 | TS_Apollo 24/7_Lab Tests_04 | To verify adding a test to the cart, updating the cart count, and confirming the item is present in the cart.
2
3
1 | View Details Functionality | TR_Apollo 24/7_Lab Tests_05 | TS_Apollo 24/7_Lab Tests_05 | To verify the pop-up appears after adding a test to the cart, validate the “View Details” button, and confirm navigation to the details page from the pop-up.
2
3

## TestCases
|  | Application Under Test: | Apollo24/7
US_ID | TS_ID | TC_ID | Objective | Pre condition | Steps | Test Data | Expected Result | Post condition | Test Type | Actual Result | Status | Remark/Comment
US_Apollo24/7_LabTests_01 | TS_1 | TC_Apollo24/7_Lab Tests_01 | Test when user clicks on the Lab Tests link from the homepage and navigates successfully to the Lab Tests page. Given: The user is on the Apollo 24/7 homepage. When: The user clicks on the Lab Tests link in the navigation menu. Then: The Lab Tests page should load successfully, displaying all expected elements. | 1.The Apollo24/7 application is launched successfully. 2.The homepage of Apollo24/7 is displayed on the screen. | 1.Open Apollo24/7 Homepage in browser 2.click on Lab Tests option 3.Verify Lab Tests page is displayed | https://www.apollo247.com/ | It should land to Lab Tests page | Lab Test page opened successfully | Functional Testing | Lab Test page opened successfully | Passed | All the test steps were successfully executed, and the expected results were achieved.
|  | TC_Apollo24/7_Lab Tests_02 | Test when the Lab Tests page loads completely after navigation from the homepage. Given: The user has clicked on the Lab Tests link from the Apollo 24/7 homepage. When: The Lab Tests page starts loading. Then: All expected elements on the Lab Tests page should be displayed correctly and the page should load without errors. | 1The user has successfully clicked on the Lab Tests link from the Apollo24/7 homepage. 2.The Lab Tests page is fully loaded and visible on the screen with all expected elements. | 1.check page elements 2.Verify all expected elements are loaded | N/A | It should load Page elements | Page elements loaded correctly | Functional Testing | Page elements loaded correctly | Passed | All the test steps were successfully executed, and the expected results were achieved.
|  | TC_Apollo24/7_Lab Tests_03 | Test when the user clicks on the “View All” button under Top Booked Tests and navigates successfully to the full list of tests. Given: The user is on the Lab Tests page of Apollo 24/7. When: The user clicks on the “View All” button under the Top Booked Tests section. Then: The system should display the full list of Top Booked Tests on a new page without errors. | 1The user has successfully clicked on the Lab Tests link from the Apollo24/7 homepage. 2.The Lab Tests page is fully loaded and visible on the screen with all expected elements. | 1.click on View All under Top Booked Tests 2.Verify all tests are displayed | click View All | It should land to View All page | View All page opened successfully | Functional Testing | View All page opened successfully | Passed | All the test steps were successfully executed, and the expected results were achieved.
US_Apollo24/7_LabTests_02 | TS_2 | TC_Apollo24/7_Lab Tests_04 | Test for TS Apollo24/7 Lab Tests 02. Given: View All page is open. When: 1.check list after View All 2.Verify list contains all tests. Then: Expected result should occur. | 1. The user has successfully clicked on the View All link from the Apollo24/7 homepage. 2. The View All page is fully loaded and visible on the screen with all expected elements. | 1.check list after View All 2.Verify list contains all tests | N/A | It should display all tests | All tests displayed correctly | Functional Testing | All tests displayed correctly | Passed | All the test steps were successfully executed, and the expected results were achieved.
|  | TC_Apollo24/7_Lab Tests_05 | Test for TS Apollo24/7 Lab Tests 02. Given: View All page is open. When: 1.click on Sort By dropdown 2.Verify dropdown options are visible. Then: Expected result should occur. | 1. The user has successfully clicked on the View All link from the Apollo24/7 homepage. 2. The View All page is fully loaded and visible on the screen with all expected elements. | 1.click on Sort By dropdown 2.Verify dropdown options are visible | click Sort by | Dropdown options should be visible | Dropdown options are visible | Functional Testing | Dropdown options are visible | Passed | All the test steps were successfully executed, and the expected results were achieved.
|  | TC_Apollo24/7_Lab Tests_06 | Test for TS Apollo24/7 Lab Tests 02. Given: View All page is open. When: 1.click on Price:Low to High 2.Verify tests are sorted in ascending order. Then: Expected result should occur. | 1. The user has successfully clicked on the View All link from the Apollo24/7 homepage. 2. The View All page is fully loaded and visible on the screen with all expected elements. | 1.click on Price:Low to High 2.Verify tests are sorted in ascending order | click Price :Low to High | Tests should be sorted in ascending order | Tests sorted in ascending order | Functional Testing | Tests sorted in ascending order | Passed | All the test steps were successfully executed, and the expected results were achieved.
|  | TC_Apollo24/7_Lab Tests_07 | Test for TS Apollo24/7 Lab Tests 02. Given: View All page is open. When: 1.check order of tests 2.Verify sorting applied correctly. Then: Expected result should occur. | 1. The user has successfully clicked on the View All link from the Apollo24/7 homepage. 2. The View All page is fully loaded and visible on the screen with all expected elements. | 1.check order of tests 2.Verify sorting applied correctly | N/A | Order should be correct | Order displayed correctly | Functional Testing | Order displayed correctly | Passed | All the test steps were successfully executed, and the expected results were achieved.
| TS_3 | TC_Apollo24/7_Lab Tests_08 | Test for TS Apollo24/7 Lab Tests 03. Given: View All page is open. When: 1.click on Top Deals checkbox 2.Verify Top Deals filter is applied. Then: Expected result should occur. | 1. The user has successfully clicked on the View All link from the Apollo24/7 homepage. 2. The View All page is fully loaded and visible on the screen with all expected elements. | 1.click on Top Deals checkbox 2.Verify Top Deals filter is applied | click Top Deals | Top Deals filter should be applied | Top Deals filter applied successfully | Functional Testing | Top Deals filter applied successfully | Passed | All the test steps were successfully executed, and the expected results were achieved.
|  | TC_Apollo24/7_Lab Tests_09 | Test for TS Apollo24/7 Lab Tests 03. Given: View All page is open. When: 1.click on Tests checkbox 2.Verify Tests filter persists. Then: Expected result should occur. | 1. The user has successfully clicked on the View All link from the Apollo24/7 homepage. 2. The View All page is fully loaded and visible on the screen with all expected elements. | 1.click on Tests checkbox 2.Verify Tests filter persists | click Tests | Tests filter should persist | Tests filter disappeared | Functional Testing | Tests filter disappeared | Failed | Issue observed during execution.
|  | TC_Apollo24/7_Lab Tests_10 | Test for TS Apollo24/7 Lab Tests 03. Given: View All page is open. When: 1.click on Packages checkbox 2.Verify Packages filter persists. Then: Expected result should occur. | 1. The user has successfully clicked on the View All link from the Apollo24/7 homepage. 2. The View All page is fully loaded and visible on the screen with all expected elements. | 1.click on Tests checkbox 2.Verify Tests filter persists | click Packages | Packages filter should persist | Packages filter disappeared | Functional Testing | Packages filter disappeared | Failed | Issue observed during execution.
|  | TC_Apollo24/7_Lab Tests_11 | Test for TS Apollo24/7 Lab Tests 03. Given: View All page is open. When: 1.click on multiple filters checkboxes under Type of Tests 2.Verify all filters persist. Then: Expected result should occur. | 1. The user has successfully clicked on the View All link from the Apollo24/7 homepage. 2. The View All page is fully loaded and visible on the screen with all expected elements. | 1.click on Packages checkbox 2.Verify Packages filter persists | N/A | All filters should persist | Some filters disappeared | Functional Testing | Some filters disappeared | Failed | Issue observed during execution.
US_Apollo24/7_LabTests_03 | TS_4 | TC_Apollo24/7_Lab Tests_12 | Test for TS Apollo24/7 Lab Tests 04. Given: View All page is open. When: 1.click on add on a test 2.Verify test is added to cart. Then: Expected result should occur. | 1. The user has successfully clicked on the View All link from the Apollo24/7 homepage. 2. The View All page is fully loaded and visible on the screen with all expected elements. | 1.click on multiple filters checkboxes under Type of Tests 2.Verify all filters persist | click Add | Test should be added to cart | Test added to cart successfully | Functional Testing | Test added to cart successfully | Passed | All the test steps were successfully executed, and the expected results were achieved.
|  | TC_Apollo24/7_Lab Tests_13 | Test for TS Apollo24/7 Lab Tests 04. Given: Pop-up visible. When: 1.check cart count 2.Verify cart count updated correctly. Then: Expected result should occur. | 1. The user has successfully triggered an action that displays the pop-up . 2. The pop-up is fully loaded and visible on the screen with all expected elements. | 1.click on add on a test 2.Verify test is added to cart | N/A | Cart count should be updated | Cart count updated correctly | Functional Testing | Cart count updated correctly | Passed | All the test steps were successfully executed, and the expected results were achieved.
|  | TC_Apollo24/7_Lab Tests_14 | Test for TS Apollo24/7 Lab Tests 04. Given: Pop-up visible. When: 1.check cart count 2.Verify cart count updated correctly. Then: Expected result should occur. | "1. The user has successfully triggered an action that displays the pop-up . 2. The pop-up is fully loaded and visible on the screen with all expected elements." | 1.check cart count 2.Verify cart count updated correctly | N/A | Item should be present in cart | Item present in cart | Functional Testing | Item present in cart | Passed | All the test steps were successfully executed, and the expected results were achieved.
| TS_5 | TC_Apollo24/7_Lab Tests_15 | Test for TS Apollo24/7 Lab Tests 05. Given: Pop-up visible. When: 1.Observe bottom pop-up 2.Verify pop-up appears succeessfully. Then: Expected result should occur. | "1. The user has successfully triggered an action that displays the pop-up . 2. The pop-up is fully loaded and visible on the screen with all expected elements." | 1.Observe bottom pop-up 2.Verify pop-up appears succeessfully | Observe pop-up | Pop-up should appears | Pop-up appeared successfully | Functional Testing | Pop-up appeared successfully | Passed | All the test steps were successfully executed, and the expected results were achieved.
|  | TC_Apollo24/7_Lab Tests_16 | Test for TS Apollo24/7 Lab Tests 05. Given: Pop-up visible. When: 1. click View Details in pop-up 2.Verify navigation to details page. Then: Expected result should occur. | "1. The user has successfully triggered an action that displays the pop-up . 2. The pop-up is fully loaded and visible on the screen with all expected elements." | 1. click View Details in pop-up 2.Verify navigation to details page | click View Details | It should navigate to details page | Navigated to details page successfully | Functional Testing | Navigated to details page successfully | Passed | All the test steps were successfully executed, and the expected results were achieved.
|  | TC_Apollo24/7_Lab Tests_17 | Test for TS Apollo24/7 Lab Tests 05. Given: Pop-up visible. When: 1.check details page content 2.Verify all expected content loads correctly. Then: Expected result should occur. | "1. The user has successfully triggered an action that displays the pop-up . 2. The pop-up is fully loaded and visible on the screen with all expected elements." | 1.check details page content 2.Verify all expected content loads correctly | N/A | Details page should loads corectly | Details page loaded correctly | Functional Testing | Details page loaded correctly | Passed | All the test steps were successfully executed, and the expected results were achieved.

## Defect Report
Defect Report
DefectId | Summary | Description | Build Version | Steps to reproduce | Expected Behavior | Actual Behavior | Priority | Severity | Reported By | Reported On | Assigned To | Current Status | Environment
DF_Apollo24/7_LabTests_01 | Tests filter disappears after selection | When the user selects a specific test filter on the Lab Tests page, the filter option disappears instead of remaining visible. This prevents users from knowing which filter is currently applied. | Lab Tests Module (v1.0) | 1.Navigate to the Apollo24/7 homepage. 2.Click on the Lab Tests link. 3.Apply a filter under Tests category. 4.Observe the filter behavior after selection. | The selected filter should remain visible and active until the user manually removes it. | The filter disappears immediately after selection, making it unclear which filter is applied. | High | High | Sneha Naraboina | 2025-11-10 | qa_team@apollo247.com | New | Various browers like edge,chrome, Windows 11
DF_Apollo24/7_LabTests_02 | Packages filter disappears after selection | When the user selects a package filter, the filter option disappears instead of persisting. This impacts usability and clarity for users applying multiple filters. | Lab Tests Module (v1.0) | 1Navigate to the Apollo24/7 homepage. 2.Click on the Lab Tests link. 3.Apply a filter under Packages category. 4.Observe the filter behavior after selection. | The selected package filter should remain visible and active until removed by the user. | The filter disappears immediately after selection. | High | High | Sneha Naraboina | 2025-11-10 | qa_team@apollo247.com | New | Various browers like edge,chrome, Windows 11
DF_Apollo24/7_LabTests_03 | Multiple filters do not persist when applied together | When users apply multiple filters (e.g., Tests + Packages), the previously applied filter disappears, preventing combined filtering. | Lab Tests Module (v1.0) | 1.Navigate to the Apollo24/7 homepage. 2.Click on the Lab Tests link. 3.Apply a filter under Tests category. 4.Apply another filter under Packages category. 5.Observe whether both filters remain active. | All applied filters should persist and work together until removed by the user. | Only the last applied filter remains; previous filters disappear | High | High | Sneha Naraboina | 2025-11-10 | qa_team@apollo247.com | New | Various browers like edge,chrome, Windows 11

## RTM
Requirement Traceability Matrix
BR_ID | TR_ID | TS_ID | TC_ID | Status | DR_ID
BR_Apollo24/7_LabTests_02 | REQ_Apollo24/7_LabTests_01 | TS_Apollo24/7_LabTests_01 | TC_Apollo24/7_LabTests_01 | Passed | N/A
|  |  | TC_Apollo24/7_LabTests_02 | Passed | N/A
| REQ_Apollo24/7_LabTests_02 | TS_Apollo24/7_LabTests_02 | TC_Apollo24/7_LabTests_03 | Passed | N/A
|  |  | TC_Apollo24/7_LabTests_04 | Passed | N/A
| REQ_Apollo24/7_LabTests_03 | TS_Apollo24/7_LabTests_03 | TC_Apollo24/7_LabTests_05 | Passed | N/A
|  |  | TC_Apollo24/7_LabTests_06 | Passed | N/A
|  |  | TC_Apollo24/7_LabTests_07 | Passed | N/A
| REQ_Apollo24/7_LabTests_04 | TS_Apollo24/7_LabTests_04 | TC_Apollo24/7_LabTests_08 | Passed | N/A
|  |  | TC_Apollo24/7_LabTests_09 | Failed | DF_Apollo24/7_LabTests_01
|  |  | TC_Apollo24/7_LabTests_10 | Failed | DF_Apollo24/7_LabTests_02
|  |  | TC_Apollo24/7_LabTests_11 | Failed | DF_Apollo24/7_LabTests_03
| REQ_Apollo24/7_LabTests_05 | TS_Apollo24/7_LabTests_05 | TC_Apollo24/7_LabTests_12 | Passed | N/A
|  |  | TC_Apollo24/7_LabTests_13 | Passed | N/A
|  |  | TC_Apollo24/7_LabTests_14 | Passed | N/A
| REQ_Apollo24/7_LabTests_06 | TS_Apollo24/7_LabTests_06 | TC_Apollo24/7_LabTests_15 | Passed | N/A
|  |  | TC_Apollo24/7_LabTests_16 | Passed | N/A
|  |  | TC_Apollo24/7_LabTests_17 | Passed | N/A

## Text Execution Summary
TEST EXECUTION SUMMARY
Project Name | Module Name | Total Cases | Total Passed | Total Failed | Total Executed | Pass Percentage | Fail Percentage | Complition Percentage
Apollo 24/7 | Search functionality within Lab Tests | 4 | 4 | 0 | 4 | 100% | 0% | 100%
| View All page navigation and display | 2 | 2 | 0 | 2 | 100 | 0% | 100%
| Filter functionality (Tests filter) | 4 | 3 | 1 | 4 | 75% | 25% | 100%
| Filter functionality (Packages filter) | 3 | 2 | 1 | 3 | 66.67% | 33.33% | 100%
| Multiple filters applied together | 2 | 1 | 1 | 2 | 50% | 50% | 100%
| Pop-up display and interaction | 2 | 2 | 0 | 2 | 100% | 0 | 100%

## Summary Report
Test Summary Report format
1.Test Objective: | This document captures the various activities performed as part of testing the Apollo 24/7 Lab Tests module, including navigation to Lab Tests, View All functionality, Sort By dropdown, Filters application, Cart operations, and View Details navigation.
2.Application Overview : | The Apollo 24/7 Lab Tests module allows users to browse and book diagnostic tests online. It provides features such as: Viewing all available lab tests Sorting tests by price or popularity Applying filters like Top Deals, Tests, and Packages Adding tests to the cart and checking out Viewing detailed information about selected tests
3.Testing Scope:
In-Scope: | Testing for the following are in scope:
View All functionality
Sort By dropdown (Price: Low to High)
Filters (Top Deals, Tests, Packages)
Cart functionality (Add to cart, cart count update)
View Details navigation from pop-up
Functional validations (Positive & Negative)
Out of Scope: | Admin-side job posting workflows
Areas not covered: | Following areas are not covered:
Email notifications
Accessibility testing
Mobile responsiveness
Integration with external diagnostic platforms
4.Test Metrices:
Total number of test cases planned: | 17
Total number of Test cases Executed: | 17
Total number of Test cases Passed: | 14
Total number of Test cases Failed: | 3
Total number of Test cases Planned | Total number of Test cases Executed | Total number of Test cases Passed | Total number of Test cases Failed | Remark
17 | 17 | 14 | 3 | Failures observed in filter persistence scenarios.
Graphical representation:
Requirement Traceability Matrix
BR_ID | TR_ID | TS_ID | TC_ID | Status | DR_ID
BR_Apollo24/7_LabTests_02 | REQ_Apollo24/7_LabTests_01 | TS_Apollo24/7_LabTests_01 | TC_Apollo24/7_LabTests_01 | Passed | N/A
|  |  | TC_Apollo24/7_LabTests_02 | Passed | N/A
| REQ_Apollo24/7_LabTests_02 | TS_Apollo24/7_LabTests_02 | TC_Apollo24/7_LabTests_03 | Passed | N/A
|  |  | TC_Apollo24/7_LabTests_04 | Passed | N/A
| REQ_Apollo24/7_LabTests_03 | TS_Apollo24/7_LabTests_03 | TC_Apollo24/7_LabTests_05 | Passed | N/A
|  |  | TC_Apollo24/7_LabTests_06 | Passed | N/A
|  |  | TC_Apollo24/7_LabTests_07 | Passed | N/A
| REQ_Apollo24/7_LabTests_04 | TS_Apollo24/7_LabTests_04 | TC_Apollo24/7_LabTests_08 | Passed | N/A
|  |  | TC_Apollo24/7_LabTests_09 | Failed | DF_Apollo24/7_LabTests_01
|  |  | TC_Apollo24/7_LabTests_10 | Failed | DF_Apollo24/7_LabTests_02
|  |  | TC_Apollo24/7_LabTests_11 | Failed | DF_Apollo24/7_LabTests_03
| REQ_Apollo24/7_LabTests_05 | TS_Apollo24/7_LabTests_05 | TC_Apollo24/7_LabTests_12 | Passed | N/A
|  |  | TC_Apollo24/7_LabTests_13 | Passed | N/A
|  |  | TC_Apollo24/7_LabTests_14 | Passed | N/A
| REQ_Apollo24/7_LabTests_06 | TS_Apollo24/7_LabTests_06 | TC_Apollo24/7_LabTests_15 | Passed | N/A
|  |  | TC_Apollo24/7_LabTests_16 | Passed | N/A
|  |  | TC_Apollo24/7_LabTests_17 | Passed | N/A
5.Types of testing performed
Functionality Testing | Functional testing is a type of software testing that verifies that a system or application functions correctly according to its specifications or requirements. This type of testing focuses on testing the functionality of the software and ensuring that it behaves as expected from the end user's perspective.
6.Test Environment and Tools Used:
Application URL | https://www.apollo247.com
Database | N/A
Tools Used | MS Excel(for test case management), Selenium + TestNG (for automation)
7.Recommendations and Suggestions: | Improve filter persistence functionality (Tests, Packages, Multiple filters) as these failed during execution. Conduct additional regression testing after fixing filter-related defects. Encourage user feedback through surveys and usability studies to enhance the Lab Tests experience.
8.Exit Criteria: | 1. All the test cases that were planned are executed successfully.
2.No critical defects impacting core functionality (navigation, sorting, cart, and view details) remain open.
3.All identified issues are documented with clear steps to reproduce and assigned for resolution.
9.Sign Off: | Considering the nature of the identified defects (filter persistence issues) as high priority but not blocking core booking flow, and the successful completion of all other planned test cases, the testing team recommends proceeding with the release of the Lab Tests module. Filter-related fixes can be scheduled for the next sprint.